## Slide 1
ACMPRO · FREE RESOURCE
PM Metrics Dashboard
A ready-to-present portfolio status deck — SPI, CPI, RAG health, budget burn and risk exposure — built from a companion Excel data file so you can swap in your own project numbers.
SPI
CPI
% COMPLETE
RAG STATUS
BUDGET BURN
RISK EXPOSURE
5
Projects Tracked
0.92
Portfolio SPI
0.95
Portfolio CPI
61%
Weighted % Complete
3G / 1A / 1R
RAG Mix
ACMPro.in · PM Metrics Dashboard · Free Resource · Illustrative sample data

## Slide 2
01 — Portfolio Status
Where the portfolio stands today
Report Date: 21-Jul-2026
0.92
Portfolio SPI
0.95
Portfolio CPI
61%
% Complete (Weighted)
64%
Avg. Budget Utilization
92
Total Risk Exposure
Project-Level Detail
Project | RAG | SPI | CPI | % Complete | Budget Util. | Milestone Status
Project Helix | Green | 1.06 | 1.10 | 78% | 71% | On Track — UAT Sign-off
Project Beacon | Amber | 0.91 | 0.93 | 68% | 73% | At Risk — Data Migration Complete
Project Summit | Green | 1.05 | 1.11 | 47% | 42% | On Track — Pilot Launch
Project Orbit | Red | 0.78 | 0.81 | 52% | 64% | Late — Vendor Integration Go-Live
Project Anchor | Green | 0.97 | 1.03 | 57% | 55% | On Track — Phase 2 Rollout
RAG rule: Green when SPI and CPI are both ≥ 0.95, Red when either drops below 0.85, otherwise Amber.
ACMPro.in · PM Metrics Dashboard · Free Resource · Illustrative sample data

## Slide 3
02 — Trends & Risk
Six-month trend, budget burn and where the risk sits
Portfolio SPI & CPI — 6-Month Trend
Chart: 
| Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26
SPI | 1.02 | 1 | 0.97 | 0.95 | 0.94 | 0.92
CPI | 1.05 | 1.02 | 0.99 | 0.97 | 0.95 | 0.95
Risk Exposure by Category
Chart: 
| Schedule | Cost | Resource | Scope | External
Exposure | 26 | 16 | 27 | 8 | 15
Cumulative Budget Burn (₹ Lakh)
Chart: 
| Feb-26 | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26
Planned | 120 | 165 | 205 | 245 | 280 | 307
Actual | 110 | 158 | 195 | 230 | 265 | 296
ACMPro.in · PM Metrics Dashboard · Free Resource · Illustrative sample data

## Slide 4
03 — How To Use This
Three things to look at, in order
1
Read RAG first, numbers second
A project only earns Red when SPI or CPI drops below 0.85. Everything above that line is a conversation to have in the steering committee — not a crisis to escalate.
2
Watch the trend line, not the snapshot
A portfolio can look “green” on report date and still be sliding underneath. The 6-month SPI/CPI trend catches drift a single-date view can't.
3
Risk exposure is a ranking, not a forecast
Probability × Impact tells you where governance attention should go next — it isn't a prediction of what will actually happen.
Want the working version? The companion Excel workbook behind this deck — and the full paid dashboard with live Power BI formulas — are on acmpro.in.